LITTLE CHANAKYAS

Global Preschool

Parent App

Comprehensive Product Development Plan

| Version | 1.0 — Initial Release Plan |
| --- | --- |
| Prepared Date | March 7, 2026 |
| ERP Platform | Bodhi Board v15.5.12 (Next.js) |
| Target Platforms | iOS 15+ · Android 10+ · Progressive Web App |
| Est. Duration | 12 Months (4 Phases) |
| Classification | Proprietary & Confidential |

# 1. Executive Summary

Little Chanakyas Global Preschool, powered by the Bodhi Board ERP, currently operates a fully-featured school management backend covering students, attendance, academics, finance, transport, HR, and communication. However, parents — the most critical external stakeholders — have no dedicated mobile interface to engage with this data in real time.

This document defines the complete product plan for the Little Chanakyas Parent App: a mobile-first, multi-platform application that transforms the existing ERP data into a seamless, intuitive, and delightful parent experience. The app will serve as the primary communication and engagement channel between the school and families.

Key objectives:

- Give parents real-time visibility into their child's daily school life — attendance, meals, mood, homework, and more.

- Reduce administrative burden on school staff by enabling self-service parent actions (fee payment, leave requests, etc.).

- Strengthen school-family relationships through personalised, timely communication.

- Support multi-child families with a unified, elegant profile-switcher interface.

- Achieve full parity with the ERP's 20+ modules, exposing only parent-relevant data in a clean, age-appropriate UI.

The app is planned across 4 development phases over 12 months, with a functional MVP delivered by Month 3 and full feature parity by Month 12.

# 2. Product Vision & Strategic Goals

## 2.1  Vision Statement

"Every Little Chanakyas parent should be able to see, know, and act on everything that matters about their child's school day — in seconds, from anywhere."

## 2.2  Strategic Goals

| # | Goal | Description |
| --- | --- | --- |
| G-01 | Parent Engagement | Achieve ≥ 80% daily active usage rate among enrolled parents within 6 months of launch. |
| G-02 | Communication Speed | Reduce average school-to-parent communication time from 24 hours (manual) to under 2 minutes (push notification). |
| G-03 | Fee Collection | Increase on-time fee collection rate from current baseline to ≥ 95% by enabling in-app payment reminders and one-tap payment. |
| G-04 | Staff Efficiency | Reduce admin staff time spent on parent queries by ≥ 40% through self-service features. |
| G-05 | Data Accuracy | Parents verify and update child data (contacts, health info) directly in-app, improving ERP data quality. |
| G-06 | Retention | Improve school enrollment renewal rate by increasing parental satisfaction through transparency and engagement. |
| G-07 | Platform Coverage | Support iOS, Android, and PWA (web) to ensure no parent is excluded due to device constraints. |

# 3. User Research & Parent Personas

The Parent App serves a diverse parent community. Based on the ERP user data structure (parent fields: mother contact, father contact, primary guardian, relationship, occupation), four primary personas have been identified:

| 👩‍💼 Priya — The Working Mother Age: 32 ¦ Occupation: IT Engineer Needs: - Quick morning check: Did child eat? Is attendance marked? - Push notifications — no time to open app proactively - Weekend homework reminders for planning - Fee payment on-the-go without calling school Pain Points: - Currently calls school 3–4x/week for updates - Misses events due to no advance notification | 👨‍🏫 Rajan — The Involved Father Age: 38 ¦ Occupation: Teacher Needs: - Detailed progress reports and curriculum visibility - Direct messaging with class teacher - Child's development milestones tracking - Library and homework assignment details Pain Points: - No visibility into what is taught each day - Can't track child's reading progress remotely |
| --- | --- |
| 👵 Saraswati — The Grandparent Guardian Age: 62 ¦ Primary Caregiver Needs: - Very simple, large-text UI with clear icons - Transport bus tracking: 'Has the bus arrived?' - Health alerts: allergy / medication reminders - Emergency contact quick-dial Pain Points: - Low tech comfort — needs minimal steps - Language barrier — needs vernacular support | 💼 Aditya — The Multi-Child Parent Age: 42 ¦ Business Owner ¦ 3 children Needs: - Single app, unified dashboard for all 3 children - One-tap switch between child profiles - Consolidated fee payment for multiple admissions - Cross-child event and timetable view Pain Points: - Currently uses 3 different school portals - Notification overload with separate accounts |

# 4. Feature Scope — Complete Module Mapping

Every feature in the Parent App maps directly to a corresponding ERP module in Bodhi Board. The table below defines the full feature scope, priority, and which persona benefits most.

Priority codes: P1 = MVP (Phase 1–2)  |  P2 = Growth (Phase 3)  |  P3 = Full Feature (Phase 4)

| App Module | ERP Source | Parent-Facing Features | Priority | Persona |
| --- | --- | --- | --- | --- |
| Home Dashboard | Dashboard | - Today's summary card: attendance, mood, meal status - Quick-action tiles (Message Teacher, Pay Fee, View Homework) - Upcoming events strip (next 7 days) - Unread notification badge count - Weather & school status (school open/closed indicator) - Child photo and personalised greeting | P1 | All |
| Attendance | Students → Attendance | - Live attendance status: Present / Absent / Late - Push notification when child is marked absent - Monthly attendance calendar with colour coding - Attendance percentage and trend chart - Leave application form (notify school of absence in advance) - Attendance history download | P1 | Priya |
| Classroom Daily Log | Classroom Central | - Daily activity log: Meal eaten ✓/✗, Nap taken ✓/✗, Potty ✓/✗ - Mood indicator (Happy / Sad / Tired / Excited) with icon - Teacher's note/observation for the day - Activity summary: what the child did today - Photo/video of classroom activity (if teacher uploads) - Weekly theme display (e.g., Ocean Wonders) | P1 | Saraswati |
| Homework | Homework & Activities | - List of assigned homework with due dates - Subject, description, and attachment preview - Mark as reviewed (parent acknowledgement) - Homework completion rate chart (monthly) - Overdue homework alerts with reminders - Homework submission tracking (submitted/pending) | P1 | Rajan |
| Timetable | Timetable Management | - Child's weekly class schedule by day - Subject, time slot, and teacher name - Today's schedule highlighted on home screen - Holiday and event overlays on timetable - Period substitution notifications - Downloadable timetable PDF | P2 | Rajan |
| Progress Reports | Students → Progress Reports | - View published term/semester report cards - Subject-wise marks and grade visualisation - Teacher comments per subject - Comparison with class average (anonymised) - Download PDF report card - Year-on-year progress trend charts | P1 | Rajan |
| Development | Students → Development | - Child's developmental milestones tracker - Cognitive, Social, Physical, Language skill categories - Age-appropriate milestone checklist with status - Teacher assessment notes per milestone - Monthly development summary - Milestone achievement celebration (gamified) | P2 | Rajan |
| Health Records | Students → Health Records | - View child's health profile (blood group, allergies) - Vaccination schedule and completion status - Medical conditions and emergency instructions - School nurse visit log - Update emergency contact information - Allergy alert confirmation acknowledgement | P2 | Saraswati |
| Diary / Messages | Diary | - View diary entries posted by the teacher - Homework notes, announcements, reminders - Class-wide vs child-specific message distinction - Reply to diary entries (parent-to-teacher) - Archive and search past entries - Unread count badge | P1 | All |
| Direct Communication | Communication Module | - One-to-one chat: Parent ↔ Class Teacher - Broadcast messages from Admin to all parents - Read receipts and delivery status - File and image attachment in chat - Message templates (e.g., absent today, query about homework) - Communication history archive - Escalation path to School Admin | P1 | Priya |
| Fee & Payments | Accounts Module | - Outstanding fee balance and due date - Fee structure breakdown (tuition, transport, activity) - In-app payment via UPI, Net Banking, Card, Wallet - Payment history and digital receipt download - Fee payment reminders (7-day, 3-day, 1-day alerts) - Sibling consolidated fee view (multi-child families) - Fine/late payment tracking | P1 | Aditya |
| Transport Tracker | Transport Module | - Live GPS bus location on map - 'Bus approaching' push notification (1 km away) - 'Child boarded bus' notification - 'Child dropped home' notification - Bus route and stop timings - Driver name and contact number - Transport attendance (boarded/not boarded) | P2 | Saraswati |
| Events & Calendar | Dashboard → Upcoming Events | - School events calendar (holidays, PTMs, sports day) - Event detail: date, time, venue, description - RSVP/confirmation for parent-attendance events - Add event to phone calendar (one-tap) - Event reminders (7-day, 1-day push) - Photo gallery after events | P2 | All |
| Curriculum | Curriculum Module | - Weekly learning theme and objectives - Subjects being taught this week - Learning resources and activity suggestions for home - Reading list / book recommendations - Curriculum progress (% completed for the term) - Upcoming topics preview | P3 | Rajan |
| Extracurricular | Extracurricular Module | - Enrolled activities list (dance, music, sports) - Activity schedule and session status - Achievement badges and certificates - Activity fee tracking - New activity enrollment request - Coach/instructor contact | P3 | Aditya |
| Library | Library Module | - Books currently borrowed by child - Due date and return status - Fine for overdue books - Reading history - Recommended books list - Online book reservation request | P3 | Rajan |
| Canteen | Canteen Module | - Today's menu - Pre-order meals for the week - Canteen wallet balance and top-up - Dietary preferences and allergy filters - Daily consumption history - Low balance alert | P3 | Saraswati |
| ID Card | Students → ID Cards | - Digital student ID card - QR code for school entry scan - Share/download ID card image - Emergency contact displayed on card - Validity period indicator | P2 | All |
| Parent Requests | Parent Requests Module | - Submit leave applications with reason - Early pick-up permission request - Change of guardian / contact update request - Fee concession request - Complaint / feedback submission - Request status tracking | P2 | Priya |
| Notifications | Cross-module | - Categorised notification centre (Academic, Finance, Health, Transport) - Per-category notification preference settings - Do Not Disturb schedule - In-app notification history (90 days) - Mark read / mark all read - Deep-link from notification to exact screen | P1 | All |
| Profile & Settings | Students → Identity | - Parent profile with photo - Manage linked children (multi-child) - Update contact information - Language selection (English, Hindi, Regional) - Biometric / PIN app lock - Linked device management - Account deletion / data export (DPDP Act) | P1 | Aditya |

# 5. Information Architecture & Navigation

## 5.1  App Navigation Structure

The Parent App uses a bottom tab bar for primary navigation (5 tabs) with secondary content accessible via cards, tiles, and nested screens. This ensures maximum discoverability within 2 taps for any feature.

| 🏠 Home | 👧 My Child | 📚 Academics | 💬 Messages | ⚙️ More |
| --- | --- | --- | --- | --- |
| - Today's Summary - Quick Actions - Events Strip - Notifications - Weather/Status | - Profile - Attendance - Daily Log - Health - ID Card - Switch Child | - Homework - Timetable - Progress - Curriculum - Development - Library | - Diary - Teacher Chat - Announcements - Broadcasts | - Fee & Payments - Transport - Canteen - Events Calendar - Extracurricular - Requests - Settings |

## 5.2  Multi-Child Switcher

For parents with multiple enrolled children (a core need identified in the Aditya persona), the app features a persistent child-switcher at the top of every screen. Tapping the child avatar reveals a horizontal scroll of linked child profiles. All data on screen instantly refreshes to reflect the selected child — including Home dashboard, attendance, homework, fees, and notifications.

## 5.3  Onboarding Flow

- App launch → School search by name or code → Select 'Little Chanakyas'

- Enter registered mobile number (same as ERP) → Receive OTP via SMS → Verify

- App matches phone number to ERP parent records → Displays linked children for confirmation

- Parent confirms children → Sets up PIN / biometric lock → Enables push notifications

- Personalisation: selects language, notification preferences

- Landing on personalised Home dashboard with 'Your setup is complete!' celebration state

# 6. Key Screen Specifications

The following table defines the key elements and API requirements for every primary screen in the app.

| Screen | Purpose | Key UI Elements | ERP API / Source |
| --- | --- | --- | --- |
| Splash & Login | Authenticate parent via OTP, matching ERP phone record | - School logo + animation - Phone input with country code - OTP 6-box input (autocomplete='one-time-code') - Passkey option - 256-bit TLS badge | POST /auth/parent/send-otp POST /auth/parent/verify-otp JWT → httpOnly cookie |
| Home Dashboard | Centralised daily overview personalised per child | - Child banner with photo + mood from daily log - Attendance badge (green/red) - Meal & nap status icons - Today's first class - Fee due alert (if any) - Event countdown card - Quick action grid (6 tiles) - Notification bell with count | GET /parent/dashboard/:childId (Aggregated: attendance, log, schedule, fees, events) |
| Attendance | Full attendance history and live status | - Status pill (Present/Absent/Late) - Monthly calendar heatmap - Attendance % donut chart - Leave application floating button - Filter: This week / month / term | GET /parent/attendance/:childId POST /parent/leave-request GET /parent/attendance/history |
| Daily Log | Preschool daily care log — key differentiator for Little Chanakyas | - Date selector (default: today) - Meal card (Breakfast/Lunch/Snack with ✓/✗) - Nap duration (start–end time) - Potty log (frequency) - Mood icon (animated) - Teacher note card - Today's activity photo carousel - Weekly theme banner | GET /parent/daily-log/:childId/:date GET /parent/classroom/activities/:childId |
| Homework | Track assignments across all subjects | - Subject-coloured cards - Title, description, due date - Attachment preview (PDF, image) - Status: New / Reviewed / Submitted - Parent acknowledgement toggle - Overdue: red badge - Monthly completion bar chart | GET /parent/homework/:childId PATCH /parent/homework/:id/acknowledge |
| Progress Report | Academic performance with visual breakdowns | - Term selector dropdown - Subjects grid with grade badge - Marks out of total (bar chart) - Teacher comments (collapsible) - Class average line (anonymised) - Download PDF button - Year-over-year sparkline | GET /parent/reports/:childId?term= GET /parent/reports/:childId/download |
| Timetable | Weekly schedule with today highlighted | - Day tab strip (Mon–Sat) - Period cards with time, subject, teacher - Current period highlighted - Free periods greyed - Holiday overlay (orange) - Export to Calendar button | GET /parent/timetable/:childId GET /academics/timetable/:classId |
| Transport Tracker | Live GPS bus tracking with safety notifications | - Animated map with bus icon moving - ETA chip ('Arrives in 12 min') - Pickup/dropoff status timeline - Driver info card (name, photo, phone) - Route stop list with times - Safe arrival confirmation tick | GET /parent/transport/:childId GET /transport/bus/:busId/location WebSocket: ws://erp/transport/:busId |
| Chat — Teacher | Direct 1:1 messaging with class teacher | - WhatsApp-style message bubbles - Teacher typing indicator - Message templates quick-access - File / image attachment (max 10MB) - Read receipts (single/double tick) - Chat history search - Availability indicator (school hours) | GET /parent/chat/threads POST /parent/chat/:threadId/message WebSocket: ws://erp/chat/:threadId |
| Fee Payment | View and pay outstanding fees | - Outstanding balance highlight card - Fee category breakdown table - Payment gateway integration (Razorpay/PayU) - UPI deep link - Payment history list with receipt download - Multi-child consolidated view - Auto-pay toggle | GET /parent/fees/:childId POST /parent/fees/payment/initiate GET /parent/fees/receipts/:paymentId |
| Notifications Centre | Aggregated notification hub | - Category tabs: All / Academic / Finance / Health / Transport - Card per notification with deep-link - Swipe to dismiss - Mark all read - Preference settings link - 90-day history | GET /parent/notifications PATCH /parent/notifications/read DELETE /parent/notifications/:id |
| Health Records | View and confirm child health data | - Blood group badge - Allergy chips (red, prominent) - Vaccination timeline (completed/upcoming) - Medical conditions list - Nurse visit log - Emergency contact update form | GET /parent/health/:childId GET /students/:id/health PUT /parent/contacts/:childId |
| Events & Calendar | School calendar with RSVP | - Month/week calendar toggle - Event type colour coding - Event detail bottom sheet - RSVP button (Yes/No/Maybe) - Add to phone calendar - Post-event photo gallery | GET /parent/events?month= POST /parent/events/:id/rsvp GET /parent/events/:id/gallery |
| Profile & Settings | Manage account, children, preferences | - Parent photo + name - Linked children cards - Add child button - Language picker - Notification preferences per category - PIN / biometric toggle - Data & privacy controls - Logout button | GET /parent/profile PUT /parent/profile POST /parent/link-child DELETE /parent/account |

# 7. Technical Architecture

## 7.1  Technology Stack Recommendation

| Layer | Technology | Rationale | Alternatives |
| --- | --- | --- | --- |
| Mobile Framework | React Native (Expo SDK 52+) | Single codebase for iOS & Android. Expo managed workflow for OTA updates and push notifications. Large ecosystem and school team already uses React/Next.js. | Flutter, Ionic, Capacitor |
| State Management | Zustand + React Query (TanStack) | React Query for server state (caching, background refresh, optimistic updates). Zustand for UI state (auth, child selector, preferences). | Redux Toolkit, MobX |
| Navigation | Expo Router v4 (file-based routing) | Consistent with Next.js mental model the ERP team knows. Deep-link support built-in. Type-safe routes. | React Navigation 7 |
| API Layer | REST + WebSocket (via ERP Bodhi Board API) | REST for CRUD. WebSocket for real-time features: chat, transport tracking, live attendance. | GraphQL, tRPC |
| Authentication | OTP → JWT (httpOnly cookie via SecureStore) | Mirror ERP auth flow. Store JWT in Expo SecureStore (encrypted, not localStorage). Refresh token rotation. | Passkey (FIDO2) as alternate |
| Push Notifications | Expo Push Notifications + FCM + APNs | Expo unifies FCM (Android) and APNs (iOS). Server triggers via Bodhi Board webhook events. | OneSignal, Firebase FCM direct |
| Payments | Razorpay React Native SDK | Market leader in India, supports UPI, Net Banking, Cards, Wallets. PCI-DSS compliant. Auto-captures webhook for receipt generation. | PayU, CCAvenue, Stripe |
| Maps (Transport) | React Native Maps + Google Maps API | Real-time bus tracking. Directions, ETA calculation. Geofencing for 'bus arriving' notification. | Mapbox, OpenStreetMap |
| Offline Support | TanStack Query cache + SQLite (expo-sqlite) | Cache last 7 days of attendance, homework, timetable for offline viewing. Sync on reconnect. | WatermelonDB |
| Analytics | Mixpanel + Sentry | Mixpanel for user behaviour and feature adoption tracking. Sentry for crash reporting and performance monitoring. | Firebase Analytics, Amplitude |
| CI/CD | GitHub Actions + EAS Build (Expo) | Automated builds for iOS/Android. EAS Submit for App Store / Play Store. EAS Update for OTA patches. | Bitrise, Fastlane |
| PWA | Next.js 15 + next-pwa | Web version served from existing Bodhi Board Next.js codebase with service worker for offline and install prompt. | Vite PWA |

## 7.2  Architecture Diagram (Text Description)

The system follows a layered client-server architecture with ERP integration:

Parent App (React Native / PWA)

↕ HTTPS/JWT ↕ WebSocket

API Gateway (rate limiting, auth middleware, tenant isolation by /s/:slug)

↕ ↕ ↕ ↕

Bodhi Board ERP Core [Next.js 15 App Router + Server Actions]

├── Students Service ├── Attendance Service ├── Classroom Service

├── Academic Service ├── Finance Service ├── Transport Service

├── Communication Service └── Notification Service (FCM/APNs via Expo)

↕

Database (PostgreSQL / Supabase) ¦ File Storage (AWS S3 / Cloudflare R2)

↕

Third-party: Razorpay ¦ Google Maps ¦ Twilio SMS ¦ Firebase FCM

# 8. API Design — Parent App Endpoints

All endpoints are prefixed with /api/v1 and require Bearer JWT authentication. Tenant isolation is enforced by the :slug path parameter. Rate limiting: 100 req/min per token.

| Method | Endpoint | Description | Auth | Request / Response |
| --- | --- | --- | --- | --- |
| POST | /s/:slug/auth/parent/send-otp | Send OTP to registered mobile | Public | Body: {phone, countryCode} |
| POST | /s/:slug/auth/parent/verify-otp | Verify OTP → issue JWT pair | Public | Body: {phone, otp} → {accessToken, refreshToken, children[]} |
| POST | /s/:slug/auth/refresh | Refresh access token | Refresh JWT | → new accessToken |
| DELETE | /s/:slug/auth/logout | Invalidate token, clear session | JWT | → 204 No Content |
| GET | /s/:slug/parent/dashboard/:childId | Aggregated home dashboard data | JWT | → {attendance, dailyLog, homework[], nextEvent, feeDue} |
| GET | /s/:slug/parent/attendance/:childId | Attendance records with filter | JWT | Query: ?from=&to=&view=monthly → {records[], stats} |
| POST | /s/:slug/parent/leave-request | Submit leave application | JWT | Body: {childId, fromDate, toDate, reason, type} |
| GET | /s/:slug/parent/daily-log/:childId/:date | Classroom daily log for date | JWT | → {meals{}, nap{}, potty{}, mood, teacherNote, photos[]} |
| GET | /s/:slug/parent/homework/:childId | List homework with status | JWT | Query: ?status=pending&subject= → {items[]} |
| PATCH | /s/:slug/parent/homework/:id/acknowledge | Parent marks homework as reviewed | JWT | Body: {reviewed: true} → {status: 'reviewed'} |
| GET | /s/:slug/parent/timetable/:childId | Weekly timetable for child's class | JWT | Query: ?week=current → {days: {MON: periods[]}} |
| GET | /s/:slug/parent/reports/:childId | List available report cards | JWT | Query: ?term=&year= → {reports[]} |
| GET | /s/:slug/parent/reports/:childId/:reportId | Single report card detail | JWT | → {subjects[], comments, overall, rank} |
| GET | /s/:slug/parent/transport/:childId | Transport assignment for child | JWT | → {bus{id,number,driver}, route, stops[], status} |
| GET | /s/:slug/transport/bus/:busId/location | Live GPS coordinates | JWT | → {lat, lng, speed, eta, heading} |
| GET | /s/:slug/parent/fees/:childId | Fee summary and outstanding | JWT | → {balance, dueDate, categories[], history[]} |
| POST | /s/:slug/parent/fees/payment/initiate | Create payment order | JWT | Body: {amount, childId, feeIds[]} → {orderId, gateway_payload} |
| POST | /s/:slug/parent/fees/payment/webhook | Payment gateway callback | Signed | Body: Razorpay webhook payload |
| GET | /s/:slug/parent/chat/threads | List chat threads | JWT | → {threads: [{teacherName, lastMessage, unreadCount}]} |
| POST | /s/:slug/parent/chat/:threadId/message | Send message | JWT | Body: {text?, attachment?} → {messageId, timestamp} |
| GET | /s/:slug/parent/notifications | Notification history | JWT | Query: ?category=&limit=&page= → {items[]} |
| PATCH | /s/:slug/parent/notifications/read | Mark notifications read | JWT | Body: {ids: [] ¦ 'all'} |
| POST | /s/:slug/parent/push/register | Register FCM/APNs token | JWT | Body: {token, platform: ios¦android¦web} |
| GET | /s/:slug/parent/events | School events calendar | JWT | Query: ?month=&year= → {events[]} |
| POST | /s/:slug/parent/events/:id/rsvp | RSVP for an event | JWT | Body: {status: yes¦no¦maybe} |
| GET | /s/:slug/parent/profile | Parent profile and linked children | JWT | → {parent{}, children[]} |
| PUT | /s/:slug/parent/profile | Update parent profile | JWT | Body: {name?, email?, language?} |
| POST | /s/:slug/parent/requests | Submit parent request | JWT | Body: {type, childId, details, attachments[]} |

# 9. Push Notification Strategy

## 9.1  Notification Categories & Triggers

| Category | Trigger Event | Notification Copy Example | Timing | Priority |
| --- | --- | --- | --- | --- |
| Attendance | Child marked absent | Aarav was marked absent today. Tap to apply for leave. | Real-time | High |
| Attendance | Late arrival marked | Aarav arrived at 9:47 AM. School starts at 9:00 AM. | Real-time | Medium |
| Daily Log | Mood log posted | Aarav had a Happy day! Lunch: Ate well. Nap: 45 min. | After 3 PM | Medium |
| Homework | New homework assigned | New homework in Maths: Count 1-20. Due Friday. | On publish | Medium |
| Homework | Homework due tomorrow | Reminder: Aarav's Maths homework is due tomorrow. | 8:00 PM | High |
| Finance | Fee due in 7 days | School fee of ₹12,500 is due on 14 March. Pay now. | 7 AM on D-7 | High |
| Finance | Payment successful | Payment of ₹12,500 received. Receipt #RCP-0123. | Real-time | Medium |
| Transport | Bus 1 km away | Bus #LC-12 is 1 km away. Be ready at the stop! | Geofence | Critical |
| Transport | Child boarded bus | Aarav has boarded Bus #LC-12 at 3:52 PM. | On scan | High |
| Transport | Child dropped off | Aarav has been dropped off at your stop at 4:28 PM. | On geofence | High |
| Messages | New teacher message | Ms Priyanka sent you a message. Tap to read. | Real-time | High |
| Events | Event reminder | School Sports Day is tomorrow at 9 AM. See details. | 24h before | Medium |
| Reports | Report card published | Aarav's Term 1 report card is now available. | On publish | High |
| Health | Vaccination due | Aarav's DPT booster is due next month. See health records. | D-30 | Medium |

## 9.2  User Notification Preferences

Parents must be able to control notification granularity. The Settings screen will offer per-category toggles, quiet hours (DND schedule), and per-child notification routing. Default settings will be all-on except marketing/promotional.

# 10. Security & Privacy Design

Given the sensitive nature of children's data, the Parent App must meet the highest security standards. The following design decisions address the vulnerabilities identified in the ERP audit:

| Security Area | Requirement | Implementation |
| --- | --- | --- |
| Authentication | OTP + JWT with strict expiry | Access token: 15-minute expiry. Refresh token: 7-day expiry, rotation on use. Store in Expo SecureStore (iOS Keychain / Android Keystore) — NOT localStorage. |
| Token Storage | Never localStorage | Use expo-secure-store for JWT. Use httpOnly, Secure, SameSite=Strict cookies for PWA. Eliminates XSS token theft. |
| OTP Security | Rate limiting + brute-force protection | Max 5 OTP attempts per phone per 30 minutes. Progressive lockout: 1h, 24h. Server-side validation only. OTP valid for 5 minutes (not 10). |
| Data Transmission | TLS 1.3 minimum | Enforce TLS 1.3 for all API and WebSocket connections. Certificate pinning in the React Native app to prevent MITM attacks. |
| Content Security | CSP + HTTPS only | Implement strict CSP on PWA: default-src 'self'. Strict-Transport-Security header. No mixed content. |
| Child Data Privacy | DPDP Act 2023 compliance | Parental consent required for all data collection. Data minimisation: only display data the parent is authorised to view. Right to erasure: account deletion clears all PII within 30 days. |
| Multi-Tenant Isolation | Strict slug-based isolation | Server enforces that the JWT sub matches the school slug in every API request. Parents cannot access data from other school slugs. |
| App Security | Jailbreak/root detection | Expo's react-native-device-info for basic root/jailbreak detection. Warn user and disable sensitive features (payments) if detected. |
| Session Management | Idle timeout + device management | Auto-lock after 5 minutes inactivity. Show 'Linked Devices' in settings with ability to revoke sessions. Push notification to registered devices on new login from unrecognised device. |
| In-App Payments | PCI-DSS compliance | All payment processing via Razorpay SDK. Card data never touches our servers. Use Razorpay's hosted checkout for card payments. |
| Communication | End-to-End encrypted chat | Chat messages encrypted at rest (AES-256). Teacher-parent messages stored with per-conversation key. Teacher cannot see parent-admin messages and vice versa. |
| Analytics & Tracking | No third-party tracking of children | Mixpanel events track feature usage only — no child-identifiable data in analytics. Comply with COPPA principles. |

# 11. UX Design Principles & Accessibility

## 11.1  Design Principles

| Principle | Guideline |
| --- | --- |
| 🎨 Brand Consistency | Mirror Little Chanakyas brand: primary pink (#E8274B), warm whites, rounded corners, playful yet professional typography (Geist/Inter). |
| ⚡ Speed First | Key information visible in under 2 taps. Home dashboard loads in < 1.5 seconds. Skeleton loaders instead of spinners for perceived performance. |
| 👵 Inclusive Design | Support text sizes up to 200% without layout breakage. High contrast mode. Support screen readers (VoiceOver/TalkBack) with semantic labels. Never disable user zoom. |
| 🌍 Localisation | Support English, Hindi, and 2 regional languages (Marathi, Kannada) at launch. RTL support architecture for future expansion. All date/time formats localised. |
| 🔕 Respectful Notifications | Never send notifications between 9 PM and 7 AM (system-enforced DND). Batch low-priority notifications. Maximum 3 non-critical notifications per day per parent. |
| 🏆 Delight Moments | Celebrate child achievements: animated confetti for report cards, milestone badges, fee paid success screen. Micro-animations make routine actions feel rewarding. |
| 💡 Progressive Disclosure | Show essential info first; details on tap. Preschool log (meal/nap/mood) displayed as large colourful icons — no need to read text. Complex fee breakdowns hidden behind 'View Details'. |
| 🔄 Optimistic UI | Mark homework 'Reviewed', RSVP to events, and send messages with instant UI feedback. Roll back gracefully if server fails. Never leave parent staring at a loading spinner. |
| 📴 Offline First | Display cached data with a subtle 'Last updated X minutes ago' indicator. Queue actions performed offline and sync when reconnected. Critical info (timetable, health records) always available offline. |

## 11.2  Accessibility Compliance (WCAG 2.1 AA)

The Parent App will be built to WCAG 2.1 Level AA from the ground up, addressing all issues found in the ERP audit:

- All interactive elements have accessible names (aria-label or visible text)

- Colour contrast ratio ≥ 4.5:1 for all text

- User zoom/scaling never disabled

- Touch targets minimum 44×44 px

- Screen reader fully supported (VoiceOver on iOS, TalkBack on Android)

- Dynamic text size support (iOS Dynamic Type, Android font scale)

- Skip to main content gesture on PWA

- No content that flashes more than 3 times per second (seizure safety)

# 12. Development Phases & Roadmap

## 12.1  Phased Delivery Plan

| Phase | Name | Duration | Deliverables |
| --- | --- | --- | --- |
| 1 | Foundation & MVP | Months 1–3 (12 weeks) | Auth (OTP login, multi-child setup) · Home Dashboard · Attendance + Leave Request · Daily Log · Homework · Progress Reports · Direct Messaging · Push Notifications framework · Fee view (read-only) |
| 2 | Core Operations | Months 4–6 (12 weeks) | In-app Fee Payment (Razorpay) · Timetable · Events & Calendar · Parent Requests · Notifications Centre · Diary · Digital ID Card · Health Records view · Language localisation (Hindi) |
| 3 | Advanced Features | Months 7–9 (12 weeks) | Transport Live Tracking (GPS + WebSocket) · Development Milestones · Curriculum view · Teacher Guides for parents · Parent-Teacher Meeting booking · Report Card download PDF · Canteen menu view |
| 4 | Full Feature Parity | Months 10–12 (12 weeks) | Library tracker · Canteen pre-ordering + wallet top-up · Extracurricular management · Hostel management (if applicable) · School Store · Advanced analytics for parents · Biometric login · Multi-language expansion |

## 12.2  Month-by-Month Sprint Plan

| Month | Sprint | Key Deliverables |
| --- | --- | --- |
| M1 | Sprint 1–2 | Project setup, design system, component library, CI/CD pipeline, ERP API audit and contract definition, database schema for parent tables, wireframes signed off |
| M2 | Sprint 3–4 | OTP auth flow, JWT with SecureStore, multi-child onboarding, Home Dashboard API + UI, Attendance module (view + calendar heatmap) |
| M3 | Sprint 5–6 | Daily Log screen, Homework module with acknowledgement, Progress Report viewer, Basic push notifications (attendance, homework), Internal beta (staff + pilot parents) |
| M4 | Sprint 7–8 | Fee payment integration (Razorpay), Timetable screen, Events calendar with RSVP, Direct messaging (teacher-parent chat) |
| M5 | Sprint 9–10 | Parent Requests module, Notifications Centre with preferences, Diary screen, Digital ID Card, Health Records |
| M6 | Sprint 11–12 | Hindi localisation, PWA build, App Store & Play Store submission, Performance tuning (< 1.5s TTI), Bug bash, Public Beta (50 pilot families) |
| M7 | Sprint 13–14 | Transport GPS tracking, WebSocket for real-time updates, Geofence 'bus arriving' notifications, Development Milestones tracker |
| M8 | Sprint 15–16 | Curriculum view + weekly themes, Teacher Guides, PT Meeting booking, Offline mode (SQLite cache layer) |
| M9 | Sprint 17–18 | Report card PDF export, Canteen menu view, Analytics (Mixpanel), Sentry crash monitoring, Security audit (penetration testing) |
| M10 | Sprint 19–20 | Library module, Extracurricular management, School Store integration, Canteen pre-order + wallet |
| M11 | Sprint 21–22 | Second language localisation (Marathi/Kannada), Advanced parent analytics (attendance trends, fee history), Biometric login, Accessibility audit (WCAG 2.1 AA certification) |
| M12 | Sprint 23–24 | Final bug fixes, performance optimisation, full regression testing, App Store version 1.0 official release, Admin dashboard for school (notification analytics, engagement rates) |

# 13. Team Structure & Resource Requirements

| Role | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Key Responsibilities |
| --- | --- | --- | --- | --- | --- |
| Product Manager | 1 | 1 | 1 | 1 | Roadmap ownership, sprint planning, stakeholder communication, acceptance testing |
| UX/UI Designer | 1 | 1 | 0.5 | 0.5 | Wireframes, design system, prototype, accessibility review, brand consistency |
| React Native Developer (Senior) | 1 | 1 | 1 | 1 | Core app architecture, auth, navigation, performance, App Store deployment |
| React Native Developer (Mid) | 1 | 2 | 2 | 1 | Feature screens, component library, API integration, unit tests |
| Backend Developer (Node.js/Next.js) | 1 | 1 | 1 | 0.5 | Parent API endpoints, WebSocket server, notification service, ERP integration |
| QA Engineer | 0.5 | 1 | 1 | 1 | Test plans, manual testing, automation (Detox), regression, accessibility testing |
| DevOps Engineer | 0.5 | 0.5 | 0.5 | 0.5 | CI/CD, EAS Build, App Store automation, infrastructure, monitoring |
| Security Consultant | 0 | 0 | 0.5 | 0 | Penetration testing, DPDP Act compliance review, auth audit |
| Localisation Specialist | 0 | 0.5 | 0.5 | 0.5 | Hindi, Marathi, Kannada translation, cultural adaptation, RTL prep |

# 14. Testing Strategy

## 14.1  Test Types & Coverage

| Test Type | Tool | Coverage Target | Scope |
| --- | --- | --- | --- |
| Unit Tests | Jest + React Native Testing Library | ≥ 80% | All business logic, utility functions, state management reducers |
| Component Tests | React Native Testing Library | Key components | Form validation, child switcher, notification card, payment flow |
| Integration Tests | MSW (Mock Service Worker) | All API paths | API integration, error states, offline behaviour, OTP flow |
| E2E Tests | Detox (iOS/Android) | Critical flows | Login, attendance view, homework ack., fee payment, send message |
| Performance Tests | Flipper + Metro profiler | TTI < 1.5s | Dashboard load, list scrolling (60fps), map rendering |
| Accessibility Tests | axe-core React Native | WCAG 2.1 AA | Every screen — automated + manual with VoiceOver/TalkBack |
| Security Testing | OWASP Mobile Top 10 | All endpoints | Penetration test by Month 9: auth, storage, network, injection |
| Device Testing | Firebase Test Lab (100+ devices) | iOS 15+, Android 10+ | Top 10 devices by school parent demographics |
| UAT | Pilot: 50 parent families | Functional coverage | Week 10-12 of Phase 2 — real-world usage with feedback |

## 14.2  Critical Test Scenarios

- OTP Login: valid OTP, expired OTP, wrong OTP × 5 (lockout), OTP auto-fill from SMS, passkey flow

- Multi-child: switch between children, verify all data scopes change correctly, consolidated fee view

- Offline: view cached dashboard, attempt fee payment offline (graceful error), sync on reconnect

- Transport: live GPS simulation, geofence trigger for 'bus arriving' notification, driver contact

- Fee Payment: successful payment, payment failure, partial payment, refund display

- Push Notification: receive while app is open (in-app alert), app closed (system notification), notification deep-link to correct screen

- Security: JWT expiry enforcement, invalid slug access attempt, XSS probe in chat input, SQLi probe in search

- Accessibility: full navigation via keyboard/VoiceOver/TalkBack, text size 200% layout validation

# 15. Success Metrics & KPIs

| KPI | Target | Timeline | Measurement |
| --- | --- | --- | --- |
| App Download Rate | 100% of enrolled families within 30 days of launch | Month 1 post-launch | App Store installs + PWA installs |
| Daily Active Users (DAU) | ≥ 70% DAU/MAU ratio | Month 3 post-launch | Mixpanel DAU |
| Push Notification Open Rate | ≥ 40% (Industry avg: 3-5%) | Ongoing | FCM analytics |
| Fee Collection Timeliness | ≥ 95% on-time payments | Month 6 post-launch | Finance module ERP data |
| App Store Rating | ≥ 4.6 stars on both stores | Month 6 | App Store Connect + Play Console |
| Crash-Free Sessions | ≥ 99.5% | Ongoing | Sentry |
| Parent Query Volume to Office | ≥ 40% reduction in phone/walk-in queries | Month 6 | Admin survey |
| Attendance Notification Engagement | ≥ 85% of parents open absence notification within 5 min | Ongoing | Notification analytics |
| Homework Acknowledgement Rate | ≥ 75% of assigned homework acknowledged by parent | Month 3 | API acknowledgement data |
| Message Response Time (Teacher) | Average < 2 hours during school hours | Ongoing | Chat API timestamps |
| WCAG 2.1 AA Compliance | 100% of screens pass | Before public launch | Automated + manual audit |
| API Response Time | P95 < 300ms for dashboard endpoint | Ongoing | APM monitoring |

# 16. Risks & Mitigation Plan

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| ERP API not stable or undocumented — parent endpoints don't exist yet | High | Critical | Begin API design workshop in Month 1. Mock all APIs with MSW. Assign 1 backend developer full-time to ERP side of API contract. |
| Low parent adoption due to digital literacy barriers | Medium | High | Provide onboarding tutorial video (2 min), in-app guided tour, multilingual support, school admin dashboard to track non-adopters. |
| App Store rejection due to policy violations (children's data) | Medium | High | Follow Apple App Store and Google Play COPPA/DPDP guidelines strictly. Privacy policy reviewed by legal counsel. Kids Category handling reviewed before submission. |
| Payment gateway downtime during fee rush period | Low | High | Implement payment retry logic, offline payment intent queuing, email confirmation fallback, 24h payment gateway SLA. |
| Real-time transport tracking drains device battery | Medium | Medium | Use geofence-based updates (not continuous GPS polling). Reduce WebSocket heartbeat interval. Allow parent to disable tracking in settings. |
| ERP data quality issues (0 students in some modules, stale dates) | High | Medium | Validate and clean ERP data before connecting Parent App. Display 'data not available' states gracefully rather than empty screens or crashes. |
| Security breach exposing children's data | Low | Critical | Penetration testing, OWASP compliance, security audit every 6 months, DPDP Act compliance officer, breach response plan documented. |
| Scope creep delaying MVP | Medium | High | Strict P1/P2/P3 priority gates. Product Manager holds veto on mid-sprint scope changes. Monthly stakeholder review with signed scope acceptance. |

# 17. Appendix

## 17.1  ERP Modules Referenced

This plan was developed based on a live QA audit of the Little Chanakyas Bodhi Board ERP (v15.5.12) on March 7, 2026. The following 20+ ERP modules were directly observed and mapped:

| Academic Modules | Operations Modules | Administrative Modules |
| --- | --- | --- |
| - Students Directory - Attendance - Progress Reports - Development - Health Records - ID Cards - Classes & Sections - Classroom Central - Teacher Guides - Worksheets | - Timetable Management - Homework & Activities - Curriculum - Diary - Transport - Library - Canteen - Hostel Management - Extracurricular - School Store | - Accounts & Finance - Human Resources - Admissions CRM - Communication - Marketing Tools - Training Center - Documents - Parent Requests - User Logs - Settings (9 sub-modules) |

## 17.2  Glossary

ERP  Enterprise Resource Planning — the Bodhi Board school management system

OTP  One-Time Password — 6-digit SMS verification code for login

JWT  JSON Web Token — authentication token (should be in httpOnly cookie, NOT localStorage)

FCM  Firebase Cloud Messaging — Google's push notification service for Android

APNs  Apple Push Notification service — Apple's push notification service for iOS

PWA  Progressive Web App — web app installable on mobile devices without App Store

DAU/MAU  Daily / Monthly Active Users ratio — core engagement metric

DPDP  Digital Personal Data Protection Act 2023 — India's data privacy legislation

P95  95th percentile response time — API performance benchmark

TTI  Time to Interactive — web/app performance metric for when a page is usable

UAT  User Acceptance Testing — testing with real end users (parents) before launch

WCAG  Web Content Accessibility Guidelines — international accessibility standard

End of Document  ·  Little Chanakyas Parent App — Comprehensive Development Plan

Version 1.0  ·  March 7, 2026  ·  Proprietary & Confidential  ·  Little Chanakyas Global Preschool